## Slide 1: Thermodynamic Reassessment of Ni-Ti-Zr Ternary System

## Slide 2
Heading | Work under each heading | Remark
Literature collection | Please collect recent literature data related to Ni-Ti-Zr system | 
Critical Review | Format for critical review, note for author for ternary system and example files are given already Prepare experimental (exp) file | Helpful to identify the information which is related to phase diagram. Helpful for project report and publication
Selection of Binary system. | Identify thermodynamic description of binary systems available and its limitation. Select which description is going be used for present analysis and prepare TDB file The phases NiTi-B2 and Ti-BCC in Ni-Ti system can be expressed as order-disorder model. It is little bit complicated but possible to extern this system for Ni-Ti-Zr ternary. | 
Gibbs energy modelling | Select Gibbs energy model for binary phase which extends in ternary region Select Gibbs energy model for ternary compounds Prepare TDB file | 
Gibbs energy of ternary compound | If the crystal structure of ternary compounds are know then the end member Gibbs energy can be obtained using DFT | 
Preparation of POP file | Select data for optimization and prepare pop file | 
Optimization | Optimization to find unknown variable in TDB file Round off the value of found variables | 
Generation of phase diagram | Generate isothermal and isopleths phase diagram and super impose the experimental data. | 

## Slide 3: Software Required
Open Calphad or Thermo-Calc
If the ternary compound crystal structure is known then need software for first principle calculation else semi-emprical method has to be used.

## Slide 4: Action Plan
Month | February |  |  | March |  |  |  | April |  |  | 
Week | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th
Literature collection |  |  |  |  |  |  |  |  |  |  | 
Critical Review |  |  |  |  |  |  |  |  |  |  | 
Selection of Binary system. |  |  |  |  |  |  |  |  |  |  | 
Gibbs energy modelling |  |  |  |  |  |  |  |  |  |  | 
Preparation of POP file |  |  |  |  |  |  |  |  |  |  | 
Optimization |  |  |  |  |  |  |  |  |  |  | 
Generation of ternary phase diagram |  |  |  |  |  |  |  |  |  |  |